## Product Backlog
Planned Sprint | Actual Sprint | US ID | User Story Description | MOSCOW | Dependency | Assignee | Status
1 |  | 1 | Data Collection & Ingestion: Build scripts to ingest heterogeneous sources (CSV, PDF, Excel, Email). | MUST HAVE | - |  | 3- Completed
1 |  | 2 | Data Normalization: Clean and standardize text data for downstream processing. | MUST HAVE | 1 |  | 3- Completed
2 |  | 3 | Entity Extraction: Implement spaCy NER to identify key entities (People, Orgs, Locations). | MUST HAVE | 2 |  | 3- Completed
2 |  | 3 | Relationship Extraction: Extract and clean triples (Subject-Predicate-Object) from text. | MUST HAVE | 3 |  | 3- Completed
3 |  | 5 | Chunking & Embeddings: Generate 800-char semantic chunks and store vectors using bge-base-en-v1.5. | MUST HAVE | 2 |  | 3- Completed
4 |  | 6 | Vector Database: Build a FAISS index for high-speed semantic similarity search. | MUST HAVE | 5 |  | 3- Completed
5 |  | 7 | Neo4j Loading: Design G3 schema and load entities/relations with full document provenance. | MUST HAVE | 4 |  | 3- Completed
6 |  | 8 | RAG Pipeline: Create a hybrid retriever using Groq LLM to synthesize FAISS and Neo4j data. | MUST HAVE | 6,7 |  | 3- Completed
7 |  | 9 | Streamlit UI: Build a web-based dashboard for user queries, graph visualization, and bot responses. | MUST HAVE | 8 |  | 3- Completed
8 |  | 10 | Model Evaluation: Implement metrics to validate answer accuracy. | MUST HAVE | 8 |  | 3- Completed
8 |  | 11 | Final Documentation: Filling agile documents and pushing to github | MUST HAVE | 9,10 |  | 3- Completed
Note on F1: ====== ID#AAABcShYZQo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Mention the US ID(s) on which the user story depends.

## Sprint Backlog
NOTES: Task sizing should be between 0.5 to 12 hours
US ID | Task ID | Task Description | Task Start Date | Task Completion Date | Team Member | Activity | Status | Original Estimate Effort (In Hours) | Day 1 | Day 2 | Day 3 | Day 4 | Day 5 | Day 6 | Day 7 | Day 8 | Day 9 | Day 10 | Day 11 | Day 12 | Day 13 | Day 14
[8 empty] | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0 | 0
SPRINT 1 BACKLOG
U01 | T01 | Collect raw data from CSV, PDF, Excel, and Email sources. | 2025-11-30 | 2025-12-04 |  | Data Collection | 3- Completed
U01 | T02 | Implement data ingestion scripts to standardize disparate formats. | 2025-12-04 | 2025-12-08 |  | Coding | 3- Completed
U02 | T03 | Perform text normalization (lowercase, noise removal, space collapse). | 2025-12-08 | 2025-12-13 |  | Coding | 3- Completed
U03 | T04 | Integrate spaCy NER for automated entity identification (People, Orgs). | 2025-12-14 | 2025-12-18 |  | Coding | 3- Completed
U04 | T05 | Extract semantic triples (Subject-Predicate-Object) from text. | 2025-12-18 | 2025-12-22 |  | Coding | 3- Completed
U04 | T06 | Implement a cleaning pipeline to remove invalid or pronoun-based relations. | 2025-12-22 | 2025-12-27 |  | Coding | 3- Completed
U05 | T07 | Generate 800-char semantic chunks and bge-base embeddings. | 2025-12-28 | 2026-01-02 |  | Coding | 3- Completed
U06 | T08 | Build and index a FAISS vector database for semantic similarity. | 2026-01-02 | 2026-01-06 |  | Coding | 3- Completed
U07 | T09 | Populate Neo4j with clean triples using a G3 provenance schema. | 2026-01-06 | 2026-01-10 |  | Coding | 3- Completed
U08 | T10 | Setup Groq API and integrate Llama-3/Mixtral for inference. | 2026-01-11 | 2026-01-15 |  | Integration | 3- Completed
U09 | T11 | Build a hybrid RAG retriever combining FAISS results and Neo4j paths. | 2026-01-15 | 2026-01-20 |  | Coding | 3- Completed
U09 | T12 | Refine prompt engineering to ensure grounded, factual answers. | 2026-01-20 | 2026-01-24 |  | Design | 3- Completed
U10 | T13 | Develop Streamlit frontend with a Chat interface and Graph viewer. | 2026-01-25 | 2026-01-30 |  | Design | 3- Completed
U11 | T14 | Implement evaluation metrics (Recall@K, accuracy tests). | 2026-01-30 | 2026-02-03 |  | System Test | 3- Completed
Note on D2: ====== ID#AAABcShYZRI Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on E2: ====== ID#AAABcShYZRU Please enter the dates in either of these formats (2025-01-27 09:44:41) 9/15/2016 or 15-Sep-2016
Note on I3: ====== ID#AAABcShYZQ4 Sumeet Kumar Barua08 (2025-01-27 09:44:41) This is the total task estimated in hours for all the user stories
Note on J3: ====== ID#AAABcShYZRc Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 1 work
Note on K3: ====== ID#AAABcShYZRg Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 2 work
Note on L3: ====== ID#AAABcShYZQs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 3 work
Note on M3: ====== ID#AAABcShYZRo Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 4 work
Note on N3: ====== ID#AAABcShYZQw Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 5 work
Note on O3: ====== ID#AAABcShYZRk Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 6 work
Note on P3: ====== ID#AAABcShYZRY Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 7 work
Note on Q3: ====== ID#AAABcShYZRA Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 8 work
Note on R3: ====== ID#AAABcShYZRs Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 9 work
Note on S3: ====== ID#AAABcShYZRM Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 10 work
Note on T3: ====== ID#AAABcShYZRE Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 11 work
Note on U3: ====== ID#AAABcShYZQ8 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 12 work
Note on V3: ====== ID#AAABcShYZQ0 Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 13 work
Note on W3: ====== ID#AAABcShYZRQ Sumeet Kumar Barua08 (2025-01-27 09:44:41) Pending effort hours after completion of day 14 work

## Stand up Meeting
Sprint | Day | Impediments | Action Taken
Sprint | Date | Impediments (Challenges) | Action Taken (Resolution)
1 | 2025-12-02 | Heterogeneous data formats (PDF, CSV, Email) causing ingestion failures. | Developed a custom normalization pipeline to standardize text and remove metadata noise.
1 | 2025-12-09 | High volume of duplicate data detected during initial database ingestion. | Implemented validation scripts to identify schema mismatches and remove duplicate records.
2 | 2025-12-16 | NER was capturing noise from email headers and technical metadata. | Integrated spaCy with a filtration layer to focus only on People, Organizations, and Locations.
2 | 2025-12-23 | Relationship extraction resulted in invalid triples containing pronouns as subjects. | Built a cleaning script to filter out invalid predicates and ensure high-quality Subject-Predicate-Object triples.
3 | 2025-12-30 | Processing 30k+ chunks exceeded 8GB RAM capacity during embedding. | Optimized the pipeline to cap total chunks at 5,000 to maintain system stability and performance.
3 | 2026-01-06 | Neo4j graph visualization was difficult to interpret due to unlinked nodes. | Redesigned the schema to link entities to document provenance (G3 model) for better traceability.
4 | 2026-01-13 | Local LLM inference was slow and occasionally provided hallucinated answers. | Integrated Groq API for high-speed Llama-3 inference and refined prompt engineering for RAG.
4 | 2026-01-20 | Hybrid retrieval was prioritizing FAISS vectors over structured Neo4j knowledge. | Balanced the RAG pipeline to weigh graph-extracted facts equally with semantic vector results.
5 | 2026-01-27 | Streamlit UI required a responsive chat interface for real-time interaction. | Developed the final Streamlit frontend with an integrated bot and graph viewer for demo readiness.
5 | 2026-02-03 | Evaluation of metrics | Implemented Recall@K and Precision metrics to benchmark the system's performance.

## Retrospection
SL # | Sprint # | Sprint start date | Sprint end date | Team member name | Start Doing | Stop Doing | Continue Doing | Action taken
1 | 1 | 2025-11-30 | 2025-12-13 | Completed raw data collection and implemented a normalization pipeline for heterogeneous sources.
2 | 2 | 2025-12-14 | 2025-12-27 | Performed entity extraction and relationship cleaning to generate high-quality JSON triples.
3 | 3 | 2025-12-28 | 2026-01-10 | Successfully built the Neo4j Knowledge Graph and generated FAISS vector embeddings.
4 | 4 | 2026-01-11 | 2026-01-24 | Developed the hybrid RAG pipeline using Groq LPU for high-speed LLM inference.
5 | 5 | 2026-01-25 | 2026-02-08 | Deployed the final Streamlit UI with integrated graph visualization and bot chat features.
6
7