## Defects
Sl No | Submitted By | Date Submitted | Description | Detected Sprint | Assigned To | Type of Defect | Action Taken | Action Taken Date | Status | Remarks
1 | Project Team | 2025-12-05 | Ingestion failure due to unsupported PDF encryption. | 1 | Developer | Logic Error | Implemented a decryption layer using PyPDF2 to handle secure files. | 2025-12-08 | Closed
2 | Project Team | 2025-12-12 | Duplicate records appearing in the standardized JSON output. | 1 | Developer | Data Error | Added a hashing function to check for content uniqueness during normalization. | 2025-12-14 | Closed
3 | Project Team | 2025-12-20 | spaCy failing to recognize specialized technical entities. | 2 | Developer | Performance | Developed custom patterns and added them to the NER pipeline for better accuracy. | 2025-12-23 | Closed
4 | Project Team | 2026-01-02 | Memory Overflow (OOM) error when embedding 30k+ chunks on 8GB RAM. | 3 | Developer | Resource Error | Capped the embedding corpus at 5,000 priority chunks to fit hardware limits. | 2026-01-05 | Closed
5 | Project Team | 2026-01-08 | Neo4j query timeout when rendering large graph segments. | 3 | Developer | Performance | Optimized Cypher queries and added relationship indexing to improve speed. | 2026-01-10 | Closed
6 | Project Team | 2026-01-18 | LLM hallucinating answers not found in the provided context. | 4 | Developer | Logic Error | Refined prompt engineering and integrated Groq Llama-3 for better grounding. | 2026-01-22 | Closed
7 | Project Team | 2026-02-01 | Streamlit UI lagging during real-time graph visualization updates. | 5 | Developer | UI/UX Error | Implemented caching and limited the number of visible nodes in the graph viewer. | 2026-02-04 | Closed

## Sheet2
Logical
User Interface
Maintainability
Standards
Others